## WBS
Development of a fast and reliable method for ground test condition determination
Reporting |  | Presentation |  |  | Literature review/ Background analysis |  | Database development |  | Neural Network Model Development
| Bibliographic report |  | PET (dec/midterm/final) |  |  | General Theory (LTHS) |  | Stagline simulation |  | Database assembling
| PPR |  | Public presentation (midterm) |  |  | ICP - BL codes review |  | Comparative Analysis ICP <--> Stagline |  | NN structure definition
| Peer evaluation PPR |  | Public presentation (midterm) |  |  | Stagline installation |  | Identifying correction for ICP beta outputs |  | NN training
| Midterm abstract |  |  |  |  | Preparation of initial database |  | Application of the correction to a broader database |  | NN training
| Final Report Submission |  |  | Project Title |  |  |  | Stagline simulation on new conditions (from Plams. exp. Campaign) |  | NN validation
Project Phase
Activities
Delivrables

## Dates
Date | What | Deliverable
2024-11-28 | RM project Planning report with Gantt-chart (PPR)
2024-12-06 | Peer review of 2 PPRs
2024-12-16 | First project evaluation team (PET) meeting
2025-02-03 | RM bibliographic report (BR) | bibliographic report (BR) (20h of writing)
2024-03-15 | Midterm abstract updated project planning report
2024-03-17 | Midterm PET meeting
2024-03-20 | Midterm Public presentation
2024-06-10 | Submission of draft RM report
2024-06-13 | Final PET meeting
2024-06-18 | Final Public Presentation
2024-06-25 | Submission of final report

## Communication plan
Meeting | Purpose | Frequency | Participants | Status

## Risk register
Risk( Uncertainty) | Probability | Impact | Mitigation | Status | Risk identified | Status
Unavailable facility | Medium | High
Brokken material | High | Low
Conflict with existing flight software | High | High

## Sheet1 (2)
Project title
Activity title |  | Activity title |  | Activity title
| Task 1 |  | Task 1 |  | Task 1
| Task 2 |  | Task 2 |  | Task 2
| Task 3 |  | Task 3 |  | Task 3
| Task 4 |  | Task 4 |  | Task 4